## Release 2.1
QA Release 1 Plan
Agrierp module | scope | Agrierp scope doc (Testing will be done within the scope) | Agrierp test cases | Created by | Executed By | Summary
Map | No testing with any new plots. No testing with any new site/farm. Only map filters will be tested. No testing for Quick Work Order. Testing will be done with map configuration from settings only. Map testing will only be done if coordinates are available (on both Map and Work Order pages). Testing for pin location visibility on map No integration between d365 and agri | Spec - Plot Creation using KML - R1 | Map | Wania | Aqsa
Planning (with limited datasource) with Adhoc Block/Activity | Job integration will be from F&O. Stages will be defined in the Farm app. Operations integration will be from F&O. Planning lines will be adhoc. | AgriERP F&SCM - Planning | Planning Tab | Wania | Qaisar
Workorder Management (Planned) with Adhoc Block | Testing will be done on adhoc materials and resources only. Only acre and hours UOM will be used; machines will not be quantity-based. Person resources will have only hour as the unit. Work order should only be updated only before the “To Do” status, not after. Testing will include resource and machine consumption for both web and mobile. Material consumption testing for both mobile and web Resource and material adjustment testing will be done in “In Progress” work orders only. Posting will not be tested. Logs will be verified. Tank mixing will not be included. Offline testing will be done | AgriERP F&SCM-Work Order Management V1.0 | Planned workorder | Wania | wania | Total Test Cases: 51 Pending: 0 Pass: 45 Fail: 6
Workorder Management (Inspection) with Adhoc Block | Testing on template management (Attribute and inspection temp). Testing on inspection work orders. Testing on resource adjustment. Posting will not be tested. | AgriERP F&SCM - Inspection Work Order | Inspection Workorder | Wania | Wania | Inspection Work Order: Total Test Cases: 23 Pending: 22 Pass: 0 Fail: 01 Template Management: Total Test Cases: 52 Pending: 0 Pass: 51 Fail: 01
Chat & Communication | Support for image, text, audio, and document will be tested. Support for messages will be tested. Support for message notifications will be be tested. Support for group chat will be tested. | Spec - Chat and Communication | Chat & Communication | Sajid | sajid/qaiser/aqib
Dynamic level hierarchy (with limited options) | Support for grower in user profile on both mobile and web will be tested. | Nth Level Hierarchy | Dynamic level hierarchy | Wania | Wania | Total Test Cases: 31 Pending: 07 Pass: 16 Fail: 08
Attendance decoupling | Bypass attendance will be tested. No link between job hours and attendance. | Configurable Attendance Decoupling | Attendance Cases.xlsx | Wania | Wania | Total Test Cases: 45 Pending: 1 Pass: 25 Fail: 19
Universal App | Complete smoke cycle for Farm App Complete smoke cycle for Mobile App | No Document | Smoke check list.xlsx | Wania | Wania/Qaiser/Sajid/Aaqib/Aqsa
Authentication Gateway | Authentication gateway will be tested for only one company. | No Document | Authentication Gateway | Wania | Wania | Total Test Cases: 34 Pending: 14 Pass: 10 Fail: 10
Observation | Complete POI scope | No Document | POI | Wania | Wania | Total Test Cases: 37 Pending:30 Pass: 2 Fail: 5

## Release 2.2
QA Release 2 Plan
D365 module | D365 FDD | D365 Test cases | Assignee | Est time | user story
BC-ActivityJob | FDD-VB-AgriERP- Activity Job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Qaisar

## Release 2.3
QA Release 3 Plan
Agrierp module | scope | Agrierp scope doc (Testing will be done within the scope) | Agrierp test cases | Created by | Assignee | Estimation | Summary
Workorder Tank mixing | material template and workorder level support | AgriERP - Tank Mixing | Tank Mixing ¦ Test Cases ¦ Vann Brothers | Aqsa | aqsa | 30 hrs
LOT/NON LOT | Consumption support of Lot wise & Non Lot wise items Inventory Location will be entertained for the consumption Adjustment in case of changes of Inventory Location (changes will be done via SuperAdmin only) dispatch qty posting support only in thi release | AgriERP F&SCM-Work Order Management V1.0 | Inventory location | Wania | Wania | 10 hr | inprogress
D365 modules | D365 FDD | Agrierp test cases | Created by | Assignee | Summary
BC-FieldJob | FDD-VB-AgriERP- Plot job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | -- | This will not be tested until the UI is available. |  |  | VBS-FTI-000000308
Irrigation method | FDD-VB-AgriERP- Irrigation method job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | sajid | -- | This will not be tested until the UI is available. |  |  | VBS-CINV-000000114
Item Job | FDD-VB-AgriERP- Item Job.docx | Inventory location | wania | wania |  | 2 hr | blocker
Expense Job | FDD-VB-AgriERP- Expense Job.docx | Expense Job | wania | wania |  | 2 hr | blocker
Hour Job | BC-PlanningLinePostingJob-human resource -- restrict human resource hours via config | No need only check posting calls | -- | wania |  |  | done
Inventory Location Job | FDD-VB-AgriERP- Inventory location job.docx | Inventory location | Wania | wania |  | 1 hr 30 mins
Inventory App | D365 FDD | Agrierp test cases | Created by | Assignee | Summary
Inventory app | Agri Inventory Product Spec Release 2 | R2 WI - Test cases | Hammad | Hammad |  | 8 hrs
Item Dispatch-AgriINV to D365 FO (Transfer to Staging) | FDD-VB-Item Dispatch-AgriINV to D365 FO (Transfer to Staging).docx | R2 WI - Test cases | Hammad | Hammad/wania |  | 2 hr | done
Item Listing with On-hand Inventory | FDD-VB-Item Listing with On-hand Inventory | R2 WI - Test cases | Hammad | Hammad |  | 8 hrs
Item Return-AgriINV to D365 FO (Transfer to Shed) | FDD-VB-Item Return-AgriINV to D365 FO (Transfer to Shed).docx | R2 WI - Test cases | Hammad | Hammad/wania |  | 2 hr | blocker
Bug Fixes | Aqib
D365 R1 Open Items | Qaisar

## D365 Release 1
Release 1.0 Plan
D365 module | D365 FDD | D365 Test cases | Assignee | Est time | user story | User | Executed by | Status | Failed TC
BC-CropJob | FDD-VB-AgriERP- Crop job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | 1.25 |  | Sajid | Sajid | Done | 2 | Product created but not sync due to AgriERP parameters SF-ALM : Almond
BC-CropVarietyJob | FDD-VB-AgriERP- Varieties job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid |  |  |  |  | Table N/A in D365 |  | did not find this table in ERP
BC-CropMaterialGroupJob | FDD-VB-AgriERP- Crop Material group job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | 1.5 |  | Sajid | Sajid | Done |  | Crop Material group created but not synced
BC-ResourceGroupJob | FDD-VB-AgriERP- Resource group job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | 1 |  | Sajid | Sajid | Done |  | New001 Created showin on console but not sync due to AgriERP
BC-OperationJob | FDD-VB-AgriERP- Farm Operations job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid/Wania | 1.25 |  | Sajid | Sajid | Done | 3 | Operation created but not synced
BC-SeasonJob | FDD-VB-AgriERP- Crop Year job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | 1.5 |  | Sajid | Sajid | Done | 3 | Crop year is syncing and showing success logs but entry is not created on season in AgriERP.
BC-CustomerJob | FDD-VB-AgriERP- Customer Job.docx - | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | 1.5 |  | Sajid | Sajid | In progress |  | facing error: Cannot update a record in table Customers (CustTable) with Unit of Work. An attempt to change the primary key was made in the Unit of Work.
BC-UOMJob | FDD-VB-AgriERP- Unit of measure Job.docx - | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | 1.25 |  | Sajid | Sajid | Done |  | Units are showing with Material and Material is not synching. Unit logs are showing on sync Logs
BC-CreateBatchOrderJob | FDD-VB-AgriERP- Create Project Job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | QA Team
BC-MaterialJob | FDD-VB-AgriERP- Material job.docx - | Vann Phase 2-project management-Agrierp-Module-testcases | Sajid | 1.5 |  | Sajid | Sajid | Pass |  | Product is created but not synced to Farm app.
BC-ResourceJob | FDD-VB-AgriERP- Resource job.docx | Vann Phase 2-project management-Agrierp-Module-testcases | Aqib

## Release 1 customization
Features | FDD | Assignee | QA status
wip posting | FDD-VB-AgriERP-WIP Calculation | wania | Done
project category | FDD-VB-AgriERP-Project Category Setup | qaisar
resource hours | FDD-VB-AgriERP- Hour Journal – Resource Column
Extends PO line unit price decimal places to 4. |  | qaiser
Unit of measure | FDD-VB-AgriERP- Material job.docx | wania | done
Item unit of measure | FDD-VB-AgriERP- Create Project Job.docx | wania | done
FDD-VB-AgriERP-WBS Delay Days Column

## Health Report Phase 2 Release 2
S# | Apps | Modules | Test cases | Success % | Critical Bugs | High Bugs | Medium Bugs | Comments | Test Cases Execution logs | Assignee
Release 2.3
1 | AgriERP | Workorder Tank mixing | Tank Mixing ¦ Test Cases ¦ Vann Brothers | 70% |  |  |  | Testing blocked. Material template can not be created. Also, The flow works fine only when tested with ideal data. | Total cases: 94 Passed: 82 Failed: 12 Pending: 0 | aqsa/Qaiser
2 |  | LOT/ Non Lot | Inventory location | 60% |  |  |  |  | Total cases: 76 Passed: 54 Failed: 12 Pending: 10 | Wania
4 | D365 | BC Field Job | Vann Phase 2-project management-Agrierp-Module-testcases |  |  |  |  | This will not be tested until the UI is available. This is the part of the Release 4 |  | --
5 |  | Irrigation method | Vann Phase 2-project management-Agrierp-Module-testcases |  |  |  |  | This will not be tested until the UI is available. This is the part of the Release 4 |  | --
6 |  | Item Job | Inventory location |  |  |  |  | New changes are expected | Total cases: 20 Passed: 18 Failed: 2 Pending: 0 | wania
7 |  | Expense Job | Expense Job | 90% |  |  |  |  | Total cases: 20 Passed: 20 Failed: 0 Pending: 0 | wania
8 |  | Hour Job | No need only check posting calls | -- |  |  |  |  | Total cases: 0 Passed: 0 Failed: 0 Pending: 0 | wania
9 |  | Inventory Location Job | Inventory location | 60% |  |  |  | testing in progresss. waiting for bug fixes | Total cases: 10 Passed: 6 Failed: 0 Pending: 4 | wania
11 | Agri Inventory App | Item Dispatch-AgriINV to D365 FO (Transfer to Staging) | R2 WI - Test cases | 80% |  |  |  |  | Total cases: 21 Passed:19 Failed: 2 Pending: 0 | Hammad/wania
12 |  | Item Listing with On-hand Inventory | R2 WI - Test cases | 100% |  |  |  |  | Total cases: 20 Passed: 20 Failed: 0 Pending: 0 | Hammad
13 |  | Item Return-AgriINV to D365 FO (Transfer to Shed) | R2 WI - Test cases | 55% |  |  |  | This is going to redesign. Blocker | Total cases: 20 Passed: 0 Failed: 0 Pending: 0 | Hammad/wania
Release 2.2
1 | D365 | BC-ActivityJob | Vann Phase 2-project management-Agrierp-Module-testcases | 100% |  |  |  |  | Total cases: 9 Passed: 6 Failed: 0 Pending: 0 Deferred: 3 | Qaiser
Release 2.1
18 | AgriERP | Map | Map | 75% |  |  |  |  | Total cases: 106 Passed: 97 Failed: 0 Pending: 0 | Aqsa
19 |  | Planning (with limited datasource) with Adhoc Block/Activity | Planning Tab | 85% |  |  |  |  | Total cases: 20 Passed: 16 Failed: 3 Pending: 0 Deferred: 1 | Qaisar
20 |  | Workorder Management (Planned) with Adhoc Block | Planned workorder | 85% |  |  |  | Offline testcases are pending | Total Test Cases: 51 Pending: 3 Pass: 47 Fail: 1 Offline Total test cases: 34 Pending: 34 Pass: 0 Fail: 0 | wania
21 |  | Workorder Management (Inspection) with Adhoc Block | Inspection Workorder | 99% |  |  |  |  | Inspection Work Order: Total Test Cases: 23 Pending: 2 Pass: 20 Fail: 1 Template Management: Total Test Cases: 52 Pending: 0 Pass: 52 Fail: 0 | Wania
22 |  | Chat & Communication | Chat & Communication | 90% |  |  |  |  | Total cases: 35 Passed: 25 Failed: Pending: 4 | Aqib Shamim
23 |  | Dynamic level hierarchy (with limited options) | Dynamic level hierarchy | 99% |  |  |  |  | Total Test Cases: 31 Pending: 01 Pass: 29 Fail: 01 | Wania
24 |  | Attendance decoupling | Attendance Cases.xlsx | 96% |  |  |  |  | Total Test Cases: 45 Pending: 2 Pass: 40 Fail: 3 | Wania
26 |  | Authentication Gateway | Authentication Gateway | 97% |  |  |  |  | Total Test Cases: 33 Pending: 19 Pass: 11 Fail: 3 | Wania | The pending test cases are due to multi-company support not being available on VAN.
27 |  | Observation | POI | 98% |  |  |  |  | Total Test Cases: 37 Pending:0 Pass: 35 Fail: 2 | Wania