## Web and IOS Only
S# | Apps | Modules | Test cases | Success % | Critical/High Bugs | Medium Bugs | Estimates (Hr) | Comments | Test Cases Execution logs | Assignee
Release 2.3
1 | AgriERP | Workorder Tank mixing | Tank Mixing ¦ Test Cases ¦ Vann Brothers | 90% |  |  | 15 |  | Total cases: 90 Passed: 86 Failed: 0 Pending: 0 Not Applicable: 4 | Qaiser
2 |  | LOT/ Non Lot | Inventory location | 50% | Bug 23675,Bug 24139 | 2 | 10 | Return completely not working | Total cases: 76 Passed: 0 Failed: 0 Pending: 0 | Wania
6 |  | Item Job | Inventory location | 50% | 24141 |  | 2 | Not working on multiple plots | Total cases: 20 Passed: Failed: 0 Pending: 0 | wania
7 |  | Expense Job | Expense Job | 50% | 24047 | 2 | 2 | Testing could not be completed due to a high-priority bug | Total cases: 20 Passed: 0 Failed: 0 Pending: 0 | wania
8 |  | Hour Job | No need only check posting calls | -- |  |  | - |  | Total cases: 0 Passed: 0 Failed: 0 Pending: 0 | wania
11 | Agri Inventory App | Item Dispatch-AgriINV to D365 FO (Transfer to Staging) | R2 WI - Test cases |  |  |  | 2 |  | Total cases: 21 Passed:17 Failed: 2 Pending: 3 | hammad
12 |  | Item Listing with On-hand Inventory | R2 WI - Test cases |  |  |  | 2 |  | Total cases: 20 Passed: 15 Failed: 0 Pending: 5 | hammad
13 |  | Item Return-AgriINV to D365 FO (Transfer to Shed) | R2 WI - Test cases |  |  |  | 2 | This is going to redesign. Blocker | Total cases: 20 Passed: 0 Failed: 0 Pending: 0 | hammad
Release 2.2
1 | D365 | BC-ActivityJob | Vann Phase 2-project management-Agrierp-Module-testcases | 100% |  |  | 3 | Not In Scope for new client data. But it is covered in testing | Total cases: 9 Passed: 0 Failed: 0 Pending: 0 Deferred: 0 | Qaiser
Release 2.1
18 | AgriERP | Map | Map | 90% | - | 4 | 8 |  | Total cases: 106 Passed: 104 Failed: 2 Pending: 0 | Eesha Fatima
19 |  | Planning (with limited datasource) with Adhoc Block/Activity | Planning Tab | 90% |  |  | 6 |  | Total cases: 20 Passed: 18 Failed: 1 Pending: 0 Deferred: 1 | Qaisar
20 |  | Workorder Management (Planned) with Adhoc Block | Planned workorder | 60% | Bug 24190, Bug 24187 | 18 | 10 | bugs shared on email (load testing) | Total Test Cases: 51 Pending: 0 Pass: 50 Fail: 1 Except for test cases, we covered detailed testing, including exploratory testing and corner cases. | wania
21 |  | Workorder Management (Inspection) with Adhoc Block | Inspection Workorder | 40% | 24217 | 24218 24219 | 16 |  | Inspection Work Order: Total Test Cases: 23 Pending: 0 Pass: 23 Fail: 0 Template Management: Total Test Cases: 51 Pending: 0 Pass: 51 Fail: 0 | Malik
22 |  | Chat & Communication | Chat & Communication | 60% | 22787, 22793, 22900, 23571, 23668, 23669, 24232, 24233, 24234, 24235, 24236, 24237, 24238, 24239, 24240, 24241 |  | 8 |  | Total cases: 35 Passed: 0 Failed: Pending: 0 | Aqib Shamim
23 |  | Dynamic level hierarchy (with limited options) | Dynamic level hierarchy | 100% |  |  | 1 | Testing has been done only for a single location and a single grower, as support is available only for that setup. | Total Test Cases: 31 Pending: 0 Pass: 31 Fail: 0 | Wania
24 | [6 empty] | -
26 |  | Authentication Gateway | Authentication Gateway | 80% | 23887 | 22848 | 3 | The pending test cases are due to multi-company support not being available on VAN. | Total Test Cases: 33 Pending: 18 Pass: 13 Fail: 2 | Wania
27 |  | Observation | POI | 50% | 24221 |  | 6 | Only Pending Android cases | Total Test Cases: 37 Pending:0 Pass: 21 Fail: 0 | Malik
28 |  | User Role Management | User Role and Permission Test Cases |  | 24244 24243 |  | 16 |  | Total Test Cases: 84 Pending:0 Pass: 30 Fail: 0 | Qaiser/Wania
29 |  | Offline Cases | Offline Cases | 80% | 3 |  | 5 |  | Offline Total test cases: 34 Pending: 2 Pass: 0 Fail: 0 | Aqib Shamim
30 |  | Tracking logs validation. | Tracking Logs Validation | 70% |  |  | 5 |  |  | Malik
31 |  | Through testing of Admin setting screen. | Through testing of Admin setting Screen | 10% |  |  | 6 |  |  | Aqib Shamim
32 |  | Loading Testing with Multiple Plots | Testing on 10, 30 50,70 and 100 plots | 80% | - | 5 | 20 | Working on 50 and 70 plots |  | Eesha Fatima/ Wania
131 hr

## QA- Web and IOS Only
S# | Apps | Modules | Test cases | Success % | Critical/High Bugs | Medium Bugs | Comments | Test Cases Execution logs | Assignee
Release 2.3
1 | AgriERP | Workorder Tank mixing | Tank Mixing ¦ Test Cases ¦ Vann Brothers | 86% |  |  |  | Total cases: 96 Passed: 83 Failed: 1 Pending: 8 Not Applicable: 4 | Qaiser
2 |  | LOT/ Non Lot | Inventory location | 50% | Bug 23675,Bug 24139 | 2 | Return completely not working | Total cases: 76 Passed: 0 Failed: 0 Pending: 0 | Wania
6 |  | Item Job | Inventory location | 50% | 24141 |  | Not working on multiple plots | Total cases: 20 Passed: Failed: 0 Pending: 0 | wania
7 |  | Expense Job | Expense Job | 50% | 24047 | 2 | Testing could not be completed due to a high-priority bug | Total cases: 20 Passed: 0 Failed: 0 Pending: 0 | wania
8 |  | Hour Job | No need only check posting calls | -- |  |  |  | Total cases: 0 Passed: 0 Failed: 0 Pending: 0 | wania
11 | Agri Inventory App | Item Dispatch-AgriINV to D365 FO (Transfer to Staging) | R2 WI - Test cases |  |  |  |  | Total cases: 21 Passed:17 Failed: 2 Pending: 3 | hammad
12 |  | Item Listing with On-hand Inventory | R2 WI - Test cases |  |  |  |  | Total cases: 20 Passed: 15 Failed: 0 Pending: 5 | hammad
13 |  | Item Return-AgriINV to D365 FO (Transfer to Shed) | R2 WI - Test cases |  |  |  | This is going to redesign. Blocker | Total cases: 20 Passed: 0 Failed: 0 Pending: 0 | hammad
Release 2.2
1 | D365 | BC-ActivityJob | Vann Phase 2-project management-Agrierp-Module-testcases | 100% |  |  | Not In Scope for new client data. But it is covered in testing | Total cases: 9 Passed: 0 Failed: 0 Pending: 0 Deferred: 0 | Qaiser
Release 2.1
18 | AgriERP | Map | Map | 90% | - | 4 |  | Total cases: 106 Passed: 104 Failed: 2 Pending: 0 | Eesha Fatima
19 |  | Planning (with limited datasource) with Adhoc Block/Activity | Planning Tab | 90% |  |  |  | Total cases: 20 Passed: 18 Failed: 1 Pending: 0 Deferred: 1 | Qaisar
20 |  | Workorder Management (Planned) with Adhoc Block | Planned workorder | 60% | Bug 24190, Bug 24187 | 18 | bugs shared on email (load testing) | Total Test Cases: 51 Pending: 0 Pass: 50 Fail: 1 Except for test cases, we covered detailed testing, including exploratory testing and corner cases. | wania
21 |  | Workorder Management (Inspection) with Adhoc Block | Inspection Workorder | 40% | 24217 | 24218 24219 |  | Inspection Work Order: Total Test Cases: 23 Pending: 0 Pass: 23 Fail: 0 Template Management: Total Test Cases: 51 Pending: 0 Pass: 51 Fail: 0 | Malik
22 |  | Chat & Communication | Chat & Communication | 60% | 22787, 22793, 22900, 23571, 23668, 23669, 24232, 24233, 24234, 24235, 24236, 24237, 24238, 24239, 24240, 24241 |  |  | Total cases: 35 Passed: 0 Failed: Pending: 0 | Aqib Shamim
23 |  | Dynamic level hierarchy (with limited options) | Dynamic level hierarchy | 100% |  |  | Testing has been done only for a single location and a single grower, as support is available only for that setup. | Total Test Cases: 31 Pending: 0 Pass: 31 Fail: 0 | Wania
24
26 |  | Authentication Gateway | Authentication Gateway | 80% | 23887 | 22848 | The pending test cases are due to multi-company support not being available on VAN. | Total Test Cases: 33 Pending: 18 Pass: 13 Fail: 2 | Wania
27 |  | Observation | POI | 50% | 24221 |  | Only Pending Android cases | Total Test Cases: 37 Pending:0 Pass: 21 Fail: 0 | Malik
28 |  | User Role Management | User Role and Permission Test Cases |  | 24244 24243 |  |  | Total Test Cases: 84 Pending:0 Pass: 30 Fail: 0 | Qaiser/Wania
29 |  | Offline Cases | Offline Cases | 90% | 3 |  |  | Offline Total test cases: 34 Pending: 2 Pass: 0 Fail: 0 | Aqib Shamim
30 |  | Tracking logs validation. | Tracking Logs Validation | 70% |  |  |  |  | Malik
32 |  | Loading Testing with Multiple Plots | Testing on 10, 30 50,70 and 100 plots | 80% | - | 5 | Working on 50 and 70 plots |  | Eesha Fatima/ Wania